## Hoja 1
|  | HUGO | FIDAN | YAIZA
week 16 November |  | convert qr to image and read it (STEP 2, 3) | comparator (STEP 4) | Create repository and generate QR (STEP 1)
week 23 November |  | enter or not (STEP 5) | Save data (STEP 5,6) | Correct report with teacher's feedback
week 30 November |  | ALL OF US TRY TO JOIN ALL THE DIFFERENT STEPS TO ACHIEVE A COHESION AND FINISH THE CODE PART
week 7 December |  | ALL OF US PREPARE THE REPORT(WE CAN DIVIDE IT LATER) AND WE PREPARE THE SLIDES
12 Deceber |  | WE REVIEW EVERYTHING AND SUBMIT IT
13 DECEMBER | Deliver slides and report